DRC

Terms of Reference (TOR)-Annex F

for

Strategic Review of the Mixed Migration Centre (2021-2026)

# Who are the Danish Refugee Council & Mixed Migration Centre?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

MMC is a knowledge centre engaged in data collection, research, analysis, and policy and programming on mixed migration. MMC has regional hubs hosted in Africa, Asia, Europe and Latin America, with a global team headquartered in Geneva, Switzerland, and based in several countries worldwide. MMC is a leading source for independent and high-quality data, research, analysis and expertise on mixed migration. MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based protection responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. MMC’s overarching focus is on human rights and protection for all people on the move.

The MMC is part of, and governed by, the Danish Refugee Council. For more information on MMC visit our website (http://www.mixedmigration.org/).

# Purpose of the consultancy

The purpose of the consultancy is to conduct a Strategic Review of MMC performance, influence and (organisational) development during the period of 2021-2026.

# Background

MMC was established in 2018, building upon the foundation of various regional predecessors under various names and set-ups, and has since then rapidly grown into a global knowledge centre as part of the Danish Refugee Council. In 2022/23, both an external appraisal by the Danish Ministry of Foreign Affairs – which has supported MMC through various multi-year grants since its inception – and an external formative review took place. Both offered a set of recommendations to be implemented from the start of a new 3-year grant by the Danish MFA (2023-2025, with a 1-year cost extension into 2026).

Now in the last year of this most recent grant, MMC aims to conduct another strategic review of the period 2021-2026.

# Objective of the consultancy

The objective of this Strategic Review is to assess the Mixed Migration Centre’s performance, influence, and organisational development during the period 2021–2026. The Strategic Review will enable MMC to better communicate its value to key sector stakeholders and donors, as well as strengthen its strategic positioning and continue its organisational development into the future.

The Strategic Review will examine MMC’s contribution to the mixed migration field - including its contribution to Danish Refugee Council (DRC) programming and advocacy efforts -  the concrete outcomes and results produced by its work under its Theory of Change, and the extent to which it has promoted the adoption of a mixed migration lens in policy, programming, and research.

The scope of the review should be two-fold: 1) assessing the specific results achieved through Danish MFA funding during the period 2021-2026 (with a particular focus on 2023-206) and the role the support from the Danish MFA played in the development of MMC and its influence in the sector and 2) a broader review of the performance, influence, and organisational development of MMC as a whole, with the aim to identify priority areas for future development to enhance MMC’s effectiveness and sustainability.

In addition, the review should include a forward-looking component assessing the alignment between MMC’s Theory of Change and the Danish Refugee Council’s Theory of Change (finalised in 2025). This should not be treated as part of the retrospective assessment of the 2021–2026 period, but rather as a basis for recommendations to strengthen MMC’s future strategic positioning and contribution within DRC, including enhancing the integration and coherence of MMC’s activities within broader DRC programmes and strategic priorities.

# Scope of work and Methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how the objectives of the project will be achieved, and the support required from MMC and DRC. Through the proposed methodology, the review must address the following key questions:

- What unique value is MMC adding in the mixed migration field?

- To what extent has MMC successfully promoted the use and uptake of a mixed migration lens in policy, programming, and research over 2021-26? What value has this provided?

- To what extent and in what ways has MMC contributed to DRC’s programming and advocacy priorities, and how has this added value to DRC’s operations and strategic objectives?

- What concrete outcomes (as defined in its Theory of Change) has MMC achieved through its work over 2021-2026?

- To what extent has MMC improved its organisational capacity, systems, and structures over the past five years, and how has this strengthened its work?

- What strategic, organisational, or technical areas need further development to improve MMC’s influence, effectiveness and sustainability?

- To what extent is MMC’s current Theory of Change aligned with DRC’s Theory of Change, and what adjustments or opportunities should be considered to strengthen alignment and strategic coherence going forward?

The review should use mixed methods and involve primary data collection with stakeholders through key informant interviews, as well as analysis and synthesis of MMC’s preexisting internal data sources. It is expected that most interviews would occur in English, however both Spanish and French language skills may also be needed. For all questions, the review must also identify and highlight relevant outcomes and findings achieved specifically through funding from the Danish MFA.

The consultancy should produce a short review report briefly covering methodology, findings, and recommendations. Annexed to the report should be four case studies (one for each review question 1-4). These case studies should be standalone, of publishable quality and of no more than 3 pages each.

# 6. Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Task 1 | Inception report of no more than 5 pages, including annexed data collection tools | - Preparation of a detailed methodology and workplan, including data collection plan and key informant interview list, in consultation with MMC - Drafting and finalisation of data collection tools | 2 working days |
| Task 2 | Data collection and analysis | - Conducting stakeholder interviews (remote) - Analysis of interview data - Collation and analysis of internal MMC data, including Impact Reports, previous review reports, research publications, project reports, website and social media analytics, and past MEL data collection | 20 working days |
| Task 3 | Draft report including 4 case studies | - Compilation of findings and recommendations in line with the evaluation questions - Drafting case studies | 6 working days |
| Task 4 | Final report including 4 case studies + PPT deck with key findings | - Integration of feedback into final report, plus compilation of a PPT deck with key findings. | 2 working days |

The Consultant will provide the documentation by e-mail in the pertinent format.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 30 days, between April and 30th of September 2026.

Payments:

- 20% upon contract signature.

- 80% upon completion of the consultancy.

# Proposed Composition of Team

- Lead evaluator plus evaluation team (optional)

# Eligibility, qualification, and experience required

## Essential:

- Qualifications:

  - A post-graduate degree in evaluation or research or a comparable area of study

- Experience:

  - Substantial experience in monitoring, evaluation, and learning (MEL) projects, including organisation-level frameworks, tools, reviews, and evaluations.

  - Previous experience in MEL projects relating to (mixed) migration and forced migration.

  - Experience working with non-government, for-purpose, and/or charitable organisations.

  - Demonstrated experience conducting MEL interviews and/or focus groups remotely.

  - A strong and proven background (e.g. through prior publications), in producing high quality written evaluation/review reports.

- Skills and knowledge:

  - Proven MEL skills and technical expertise

  - Proven skills in mixed methods data collection and analysis

  - Excellent analytical, and reporting skills.

- Language requirements:

  - Written and spoken fluency in English, with Spanish and French desirable.

# Technical supervision

The selected consultant will work under the supervision of:

- MMC director and MMC Deputy Director

# Location and support

This is a home-based consultancy. The Consultant will provide her/his own computer and mobile telephone.

# Travel

N/A

# Submission process

Please refer to the RFP letter invitation

# Evaluation of bids

Please refer to the RFP letter invitation